# American Society for Indexing

# COMMITTEE REPORT

## Please return this report electronically no later than Tuesday, February 10, 2026.

email: gwen@asindexing.org

Name of Committee: Training Course Planning Committee	  Date: 2/10/26

Name of Chair: Shana Milkie	 Email:  smilkie@arborindexing.com

Name of Board Liaison:  Shelley Quattrocchi	 Email: qindexingservice@gmail.com

Other Committee Members (names and email addresses). Add second sheet if necessary.

Meghan Miller Brawley (meghan.m.brawley@gmail.com); Rose Coad (rmcoad@earthlink.net); Carol Reed (carolreed015@gmail.com); Jessica Siddiqi (jessicasiddiqi@gmail.com); Diana Witt (diana.witt@comcast.net)

COMPREHENSIVE REPORT OF ACTIVITY SINCE: November 5, 2025

1. The new course has launched! In coordination with the ASI Office, we did a soft launch of Modules 1 and 2 during the last week of February. As of February 9, 2026, there are three students in Module 1 and two students in Module 2, for a total of five students.

2. Shana Milkie and Jen Weers interviewed instructor candidates during December and January. We now have five instructors: Lisa Fedorak, Christine Hoskin, Amron Lehte, Cheryl Lenser, and Jessica Siddiqi. Michele Combs is also interested in being an instructor. Shana held two training sessions with the new instructors in late January.

3. Module 3 – Anna Aridome is winding down her beta testing and will submit a report soon. Module 3 is on track for a soft launch of April 2026.

4. Module 4 – 1st, 2nd, and some of the 3rd lessons (of five) have been uploaded to Moodle. All of the content for the 4th and 5th lessons has been assigned, with about 2/3 of each lesson completed. Will continue working on creating content and preparing for alpha testing. Meghan Miller Brawley is scheduled to do the alpha testing. Will recruit a beta tester. The anticipated soft launch for July of 2026 is ambitious but the committee will work very hard to make it happen.

5. Continued online discussions via Groups.io list and continued meeting approximately every six weeks via Zoom.

REQUESTED BOARD ACTION:

1. Discuss option for students to re-take the final exam if they fail a module. This would be an intermediate step before requiring them to re-take the entire module.